## GanttChart
Project Name: Heartland Equestrian Centre App
Equine Development Inc.
| Project Start Date | 2023-09-20 |  |  |  | Display Week | 15 |  | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22
[9 empty] | 2023-12-25 | [6 empty] | 2024-01-01 | [6 empty] | 2024-01-08 | [6 empty] | 2024-01-15 | [6 empty] | 2024-01-22 | [6 empty] | 2024-01-29 | [6 empty] | 2024-02-05 | [6 empty] | 2024-02-12
 | time axis 2023-12-25 to 2024-02-18
WBS | TASK |  | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2023-12-25 to 2024-02-18
1 | Initiating |  |  |  | - |  |  | -
1 | Initiating |  |  | 2023-09-20 | 2023-10-31 | 42 | 60% | 30
1.1 | Identify Stakeholders |  |  | 2023-09-20 | 2023-09-26 | 7 | 0% | 5
1.1.1 | Sign Contract with Stakeholders
1.2 | Prepare Business Case |  | 1.1 | 2023-09-27 | 2023-10-31 | 35 | 0% | 25
1.2.1 | Develop SWOT Analysis |  | 1.1 | 2023-09-27 | 2023-10-03 | 7 | 50% | 5
1.2.2 | Develop Project Background & Objectives |  | 1.2.1 | 2023-10-04 | 2023-10-09 | 6 | 0% | 4
1.2.3 | Develop Problem/Opportunity Statement |  | 1.2.2 | 2023-10-09 | 2023-10-12 | 4 | 0% | 4
1.2.4 | Develop Critical Assumptions and Constraints |  | 1.2.3 | 2023-10-13 | 2023-10-18 | 6 | 0% | 4
1.2.5 | Analyze Options and Recommendations |  | 1.2.4 | 2023-10-20 | 2023-10-25 | 6 | 0% | 4
1.2.6 | Financial Analysis |  | 1.2.5 | 2023-10-23 | 2023-10-26 | 4 | 0% | 4
2 | Planning |  |  |  | - |  |  | -
2 | Planning |  | 1.2.6 | 2023-10-27 | 2023-11-23 | 28 | 0% | 20
2.1 | Prepare Budget Estimate |  | 1.2.6 | 2023-10-27 | 2023-11-06 | 11 | 0% | 7
2.1.1 | Develop Cost Model |  | 2.1 | 2023-10-29 | 2023-11-01 | 4 | 0% | 3
2.1.2 | Develop Cost Baseline |  | 2.1 | 2023-10-29 | 2023-11-06 | 9 | 0% | 6
2.2 | Develop Scope Statement |  | 2.1.2 | 2023-11-07 | 2023-11-13 | 7 |  | 5
2.3 | Develop Project Schedule |  | 2.2 | 2023-11-14 | 2023-11-20 | 7 |  | 5
2.4 | List Potential Risks |  | 2.3 | 2023-11-17 | 2023-11-23 | 7 |  | 5
3 | Executing Plan |  |  |  | - |  |  | -
3 | Executing Plan |  | 2.4 | 2023-11-24 | 2024-01-11 | 49 | 50% | 35
3.1 | Sprint 1 |  | 2.4 | 2023-11-24 | 2023-12-06 | 13 | 0% | 9
3.1.1 | Gather Requirements |  | 3.1 | 2023-11-26 | 2023-11-29 | 4 | 0% | 3
3.1.2 | Analyze Requirements |  | 3.1.1 | 2023-11-30 | 2023-12-04 | 5 | 0% | 3
3.1.3 | Design Storyboards |  | 3.1.2 | 2023-12-02 | 2023-12-05 | 4 | 0% | 2
3.1.4 | Develop Storyboards |  | 3.1.3 | 2023-12-04 | 2023-12-06 | 3 | 0% | 3
3.2 | Sprint 2 |  | 3.1.4 | 2023-12-07 | 2023-12-19 | 13 | 0% | 9
3.2.1 | Improve Prototype |  | 3.1.4 | 2023-12-07 | 2023-12-11 | 5 | 80% | 3
3.2.2 | Develop Alpha Version |  | 3.2.1 | 2023-12-11 | 2023-12-13 | 3 | 0% | 3
3.2.3 | Test Alpha Version |  | 3.2.2 | 2023-12-15 | 2023-12-18 | 4 | 0% | 2
3.2.4 | Release Alpha Version |  | 3.2.3 | 2023-12-19 | 2023-12-19 | 1 | 0% | 1
3.3 | Sprint 3 |  | 3.2.4 | 2023-12-20 | 2024-01-01 | 13 | 0% | 9
3.3.1 | Improve Alpha Version |  | 3.2.4 | 2023-12-20 | 2023-12-22 | 3 | 0% | 3
3.3.2 | Develop Beta Version |  | 3.3.1 | 2023-12-23 | 2023-12-27 | 5 | 0% | 3
3.3.3 | Test Beta Version |  | 3.3.2 | 2023-12-28 | 2023-12-31 | 4 | 0% | 2
3.3.4 | Release Beta Version |  | 3.3.3 | 2023-12-31 | 2024-01-01 | 2 | 0% | 1
3.4 | Sprint 4 |  | 3.3.4 | 2024-01-02 | 2024-01-11 | 10 | 0% | 8
3.4.1 | Improve Beta Version |  | 3.3.5 | 2024-01-02 | 2024-01-04 | 3 | 0% | 3
3.4.2 | Develop Final Version |  | 3.4.1 | 2024-01-05 | 2024-01-08 | 4 | 0% | 2
3.4.3 | Test Final Version |  | 3.4.2 | 2024-01-08 | 2024-01-09 | 2 | 0% | 2
3.4.4 | Release Final Version |  | 3.4.3 | 2024-01-09 | 2024-01-09 | 1 | 0% | 1
4 | Monitoring & Controlling |  |  |  | - |  |  | -
4.1 | Team Meetings |  | 3.4.4 | 2024-01-10 | 2024-01-25 | 16 | 0% | 12
4.2 | Monitoring |  | 4.1 | 2024-01-10 | 2024-01-25 | 16 | 0% | 12
4.3 | Status Report |  | 4.2 | 2024-01-11 | 2024-01-26 | 16 | 0% | 12
4.4 | Documentation Changes |  | 4.2 | 2024-01-11 | 2024-01-26 | 16 | 0% | 12
5 | Closing |  |  |  | - |  |  | -
5.1 | Sign Off the Contract |  | 4.4 | 2024-01-26 | 2024-01-26 | 1 | 0% | 1
5.2 | Develop Lessons Learned Document |  | 4.4 | 2024-01-26 | 2024-01-28 | 3 | 0% | 1
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.