## Sheet1
Heartland Equestrian Centre App Schedule Network Diagram
Equine Development Inc.
# | WBS | Activity | Predecessor | Duration | Activity L ist
1 | 1 | Initiating |  | 42
2 | 1.1 | Identify Stakeholders |  | 7 | ES | D | EF | 0 | 7 | 7
3 | 1.1.1 | Sign Contract with Stakeholders |  |  | Activity Name |  |  | 1.1
4 | 1.2 | Prepare Business Case | 1.1 | 35 | LS | F | LF | 0 | 0 | 7
5 | 1.2.1 | Develop SWOT Analysis | 1.1 | 7
6 | 1.2.2 | Develop Project Background & Objectives | 1.2.1 | 6 | 7 | 7 | 14 | 14 | 6 | 20
7 | 1.2.3 | Develop Problem/Opportunity Statement | 1.2.2 | 4 | 1.2.1 |  |  | 1.2.2
8 | 1.2.4 | Develop Critical Assumptions and Constraints | 1.2.3 | 6 | 7 | 0 | 14 | 14 | 0 | 20
9 | 1.2.5 | Analyze Options and Recommendations | 1.2.4 | 6
10 | 1.2.6 | Financial Analysis | 1.2.5 | 4 | 20 | 4 | 24 | 24 | 6 | 30
11 | 2 | Planning | 1.2.6 | 28 | 1.2.3 |  |  | 1.2.4
12 | 2.1 | Prepare Budget Estimate | 1.2.6 | 11 | 20 | 0 | 24 | 24 | 0 | 30
13 | 2.1.1 | Develop Cost Model | 2.1 | 4
14 | 2.1.2 | Develop Cost Baseline | 2.1 | 9 | 30 | 6 | 36 | 36 | 4 | 40
15 | 2.2 | Develop Scope Statement | 2.1.2 | 7 | 1.2.5 |  |  | 1.2.6
16 | 2.3 | Develop Project Schedule | 2.2 | 7 | 30 | 0 | 36 | 36 | 0 | 40
17 | 2.4 | List Potential Risks | 2.3 | 7
18 | 3 | Executing Plan | 2.4 | 49 | 40 | 11 | 51 | 51 | 7 | 58
19 | 3.1 | Sprint 1 | 2.4 | 13 | 2.1 |  |  | 2.2
20 | 3.1.1 | Gather Requirements | 3.1 | 4 | 40 | 0 | 51 | 51 | 0 | 58
21 | 3.1.2 | Analyze Requirements | 3.1.1 | 5
22 | 3.1.3 | Design Storyboards | 3.1.2 | 4 | 58 | 7 | 65 | 65 | 7 | 72 | 140 Days
23 | 3.1.4 | Develop Storyboards | 3.1.3 | 3 | 2.3 |  |  | 2.4
24 | 3.2 | Sprint 2 | 3.1.4 | 13 | 58 | 0 | 65 | 65 | 0 | 72
25 | 3.2.1 | Improve Prototype | 3.1.4 | 5
26 | 3.2.2 | Develop Alpha Version | 3.2.1 | 3 | 72 | 13 | 85 | 85 | 13 | 98
27 | 3.2.3 | Test Alpha Version | 3.2.2 | 4 | 3.1 |  |  | 3.2
28 | 3.2.4 | Release Alpha Version | 3.2.3 | 1 | 72 | 0 | 85 | 85 | 0 | 98
29 | 3.3 | Sprint 3 | 3.2.4 | 13
30 | 3.3.1 | Improve Alpha Version | 3.2.4 | 3 | 98 | 13 | 111 | 111 | 10 | 121
31 | 3.3.2 | Develop Beta Version | 3.3.1 | 5 | 3.3 |  |  | 3.4
32 | 3.3.3 | Test Beta Version | 3.3.2 | 4 | 98 | 0 | 111 | 111 | 0 | 121
33 | 3.3.4 | Release Beta Version | 3.3.3 | 2
34 | 3.4 | Sprint 4 | 3.3.4 | 10 | 121 | 16 | 137 | 121 | 16 | 137
35 | 3.4.1 | Improve Beta Version | 3.3.5 | 3 | 4.1 |  |  | 4.2
36 | 3.4.2 | Develop Final Version | 3.4.1 | 4 | 121 | 0 | 137 | 121 | 0 | 137
37 | 3.4.3 | Test Final Version | 3.4.2 | 2
38 | 3.4.4 | Release Final Version | 3.4.3 | 1 | 121 | 16 | 137 | 121 | 16 | 137
39 | 4 | Monitoring & Controlling |  | 17 | 4.3 |  |  | 4.4
40 | 4.1 | Monitoring | 3.4.4 | 16 | 121 | 0 | 137 | 121 | 0 | 137
41 | 4.2 | Team Meetings | 3.4.4 | 16
42 | 4.3 | Status Report | 3.4.4 | 16 |  |  |  | 137 | 0 | 137
43 | 4.4 | Documentation Changes | 3.4.4 | 16 | Finish |  |  | 5.1
44 | 5 | Closing | [5 empty] | 140 | 3 | 140
45 | 5.1 | Sign Off the Contract | 4.4
46 | 5.2 | Develop Lessons Learned Document | 4.4 | 1 | 137 | 1 | 138 | 137 | 3 | 140
47 | 5.3 | Presentation of final product | 4.4 | 3 | 5.2 |  |  | 5.3
[5 empty] | 139 | 2 | 140 | 137 | 0 | 140
| ES | Early Start
| EF | Early Finish | EF = ES + Duration
| D | Duration | Float = Late start — Early Start
| LS | Latest Start | LS = LF— Duration
| LF | Latest Finish
| F | Float