## Sheet1
Heartland Equestrian Centre App Development Project (Budget Estimate)
Equine Development Inc.
| Prepared by: | Tamim Hasan | Date |  | 25/09/2023
[9 empty] | WBS Level 2 Total |  |  |  |  | Units/hours Calculation
# | Expense Category | Project Expenses | Units/Hours |  | Cost/Unit/Hour |  | Subtotals |  |  |  | Total | % of Total | hour/day | days/week | weeks | no. team member | total hours
1 | 1 | Initiating | [7 empty] | $ | 28800 | 11.0769
2 | 1.1 | Identify Stakeholders | [5 empty] | $ | 4800
3 | 1.1.1 | Sign Contract with Stakeholders | 40 | $ | 120 | $ | 4800 | [5 empty] | 8 | 5 | 1 | 1 | 40
4 | 1.2 | Prepare Business Case | [5 empty] | $ | 24000
5 | 1.2.1 | Develop SWOT Analysis | 40 | $ | 120 | $ | 4800 | [5 empty] | 8 | 5 | 1 | 1 | 40
6 | 1.2.2 | Develop Project Background & Objectives | 32 | $ | 120 | $ | 3840 | [5 empty] | 8 | 4 | 1 | 1 | 32
7 | 1.2.3 | Develop Problem/Opportunity Statement | 32 | $ | 120 | $ | 3840 | [5 empty] | 8 | 4 | 1 | 1 | 32
8 | 1.2.4 | Develop Critical Assumptions and Constraints | 32 | $ | 120 | $ | 3840 | [5 empty] | 8 | 4 | 1 | 1 | 32
9 | 1.2.5 | Analyze Options and Recommendations | 32 | $ | 120 | $ | 3840 | [5 empty] | 8 | 4 | 1 | 1 | 32
10 | 1.2.6 | Financial Analysis | 32 | $ | 120 | $ | 3840 | [5 empty] | 8 | 4 | 1 | 1 | 32
11 | 2 | Planning | [7 empty] | $ | 19200 | 7.3846
12 | 2.1 | Prepare Budget Estimate | [5 empty] | $ | 5760
13 | 2.1.1 | Develop Cost Model | 24 | $ | 120 | $ | 2880 | [5 empty] | 8 | 3 | 1 | 1 | 24
14 | 2.1.2 | Develop Cost Baseline | 24 | $ | 120 | $ | 2880 | [5 empty] | 8 | 3 | 1 | 1 | 24
15 | 2.2 | Develop Scope Statement | 32 | $ | 120 | $ | 3840 | $ | 3840 |  |  |  | 8 | 4 | 1 | 1 | 32
16 | 2.3 | Develop Project Schedule | 40 | $ | 120 | $ | 4800 | $ | 4800 |  |  |  | 8 | 5 | 1 | 1 | 40
17 | 2.4 | List Potential Risks | 40 | $ | 120 | $ | 4800 | $ | 4800 |  |  |  | 8 | 5 | 1 | 1 | 40
18 | 3 | Executing Plan | [7 empty] | $ | 73872 | 28.4123
19 | 3.1 | Sprint 1 | [5 empty] | $ | 21384
20 | 3.1.1 | Gather Requirements | 64.8 | $ | 90 | $ | 5832 | [5 empty] | 7.2 | 3 | 1 | 3 | 64.8
21 | 3.1.2 | Analyze Requirements | 64.8 | $ | 90 | $ | 5832 | [5 empty] | 7.2 | 3 | 1 | 3 | 64.8
22 | 3.1.3 | Design Storyboards | 43.2 | $ | 90 | $ | 3888 | [5 empty] | 7.2 | 2 | 1 | 3 | 43.2
23 | 3.1.4 | Develop Storyboards | 64.8 | $ | 90 | $ | 5832 | [5 empty] | 7.2 | 3 | 1 | 3 | 64.8
24 | 3.2 | Sprint 2 | [5 empty] | $ | 17496
25 | 3.2.1 | Improve Prototype | 64.8 | $ | 90 | $ | 5832 | [5 empty] | 7.2 | 3 | 1 | 3 | 64.8
26 | 3.2.2 | Develop Alpha Version | 64.8 | $ | 90 | $ | 5832 | [5 empty] | 7.2 | 3 | 1 | 3 | 64.8
27 | 3.2.3 | Test Alpha Version | 64.8 | $ | 90 | $ | 5832 | [5 empty] | 7.2 | 3 | 1 | 3 | 64.8
28 | 3.2.4 | Release Alpha Version | 0 | $ | 90 | $ | 0 | [5 empty] | 7.2 | 0 | 1 | 3 | 0
29 | 3.3 | Sprint 3 | [5 empty] | $ | 17496
30 | 3.3.1 | Improve Alpha Version | 64.8 | $ | 90 | $ | 5832 | [5 empty] | 7.2 | 3 | 1 | 3 | 64.8
31 | 3.3.2 | Develop Beta Version | 64.8 | $ | 90 | $ | 5832 | [5 empty] | 7.2 | 3 | 1 | 3 | 64.8
32 | 3.3.3 | Test Beta Version | 64.8 | $ | 90 | $ | 5832 | [5 empty] | 7.2 | 3 | 1 | 3 | 64.8
33 | 3.3.4 | Release Beta Version | 0 | $ | 90 | $ | 0 | [5 empty] | 7.2 | 0 | 1 | 3 | 0
34 | 3.4 | Sprint 4 | [5 empty] | $ | 17496
35 | 3.4.1 | Improve Beta Version | 64.8 | $ | 90 | $ | 5832 | [5 empty] | 7.2 | 3 | 1 | 3 | 64.8
36 | 3.4.2 | Develop Final Version | 64.8 | $ | 90 | $ | 5832 | [5 empty] | 7.2 | 3 | 1 | 3 | 64.8
37 | 3.4.3 | Test Final Version | 64.8 | $ | 90 | $ | 5832 | [5 empty] | 7.2 | 3 | 1 | 3 | 64.8
38 | 3.4.4 | Release Final Version | 0 | $ | 90 | $ | 0 | [5 empty] | 7.2 | 0 | 1 | 3 | 0
39 | 4 | Monitoring & Controlling | [7 empty] | $ | 19296 | 7.4215
40 | 4.1 | Team Meetings | [5 empty] | $ | 2592
41 | 4.1.1 | Team Meeting 1 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
42 | 4.1.2 | Team Meeting 2 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
43 | 4.1.3 | Team Meeting 3 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
44 | 4.1.4 | Team Meeting 4 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
45 | 4.1.5 | Team Meeting 5 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
46 | 4.1.6 | Team Meeting 6 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
47 | 4.1.7 | Team Meeting 7 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
48 | 4.1.8 | Team Meeting 8 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
49 | 4.1.9 | Team Meeting 9 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
50 | 4.1.10 | Team Meeting 10 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
51 | 4.1.11 | Team Meeting 11 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
52 | 4.1.12 | Team Meeting 12 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
53 | 4.2 | Monitoring | [5 empty] | $ | 11520
54 | 4.2.1 | Monitoring 1 | 8 | $ | 120 | $ | 960 | [5 empty] | 8 | 1 | 1 | 1 | 8
55 | 4.2.2 | Monitoring 2 | 8 | $ | 120 | $ | 960 | [5 empty] | 8 | 1 | 1 | 1 | 8
56 | 4.2.3 | Monitoring 3 | 8 | $ | 120 | $ | 960 | [5 empty] | 8 | 1 | 1 | 1 | 8
57 | 4.2.4 | Monitoring 4 | 8 | $ | 120 | $ | 960 | [5 empty] | 8 | 1 | 1 | 1 | 8
58 | 4.2.5 | Monitoring 5 | 8 | $ | 120 | $ | 960 | [5 empty] | 8 | 1 | 1 | 1 | 8
59 | 4.2.6 | Monitoring 6 | 8 | $ | 120 | $ | 960 | [5 empty] | 8 | 1 | 1 | 1 | 8
60 | 4.2.7 | Monitoring 7 | 8 | $ | 120 | $ | 960 | [5 empty] | 8 | 1 | 1 | 1 | 8
61 | 4.2.8 | Monitoring 8 | 8 | $ | 120 | $ | 960 | [5 empty] | 8 | 1 | 1 | 1 | 8
62 | 4.2.9 | Monitoring 9 | 8 | $ | 120 | $ | 960 | [5 empty] | 8 | 1 | 1 | 1 | 8
63 | 4.2.10 | Monitoring 10 | 8 | $ | 120 | $ | 960 | [5 empty] | 8 | 1 | 1 | 1 | 8
64 | 4.2.11 | Monitoring 11 | 8 | $ | 120 | $ | 960 | [5 empty] | 8 | 1 | 1 | 1 | 8
65 | 4.2.12 | Monitoring 12 | 8 | $ | 120 | $ | 960 | [5 empty] | 8 | 1 | 1 | 1 | 8
66 | 4.3 | Status Report | [5 empty] | $ | 2592
67 | 4.3.1 | Status Report 1 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
68 | 4.3.2 | Status Report 2 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
69 | 4.3.3 | Status Report 3 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
70 | 4.3.4 | Status Report 4 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
71 | 4.3.5 | Status Report 5 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
72 | 4.3.6 | Status Report 6 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
73 | 4.3.7 | Status Report 7 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
74 | 4.3.8 | Status Report 8 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
75 | 4.3.9 | Status Report 9 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
76 | 4.3.10 | Status Report 10 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
77 | 4.3.11 | Status Report 11 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
78 | 4.3.12 | Status Report 12 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
79 | 4.4 | Documentation Changes | [5 empty] | $ | 2592
80 | 4.1.1 | Documentation Changes 1 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
81 | 4.1.2 | Documentation Changes 2 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
82 | 4.1.3 | Documentation Changes 3 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
83 | 4.1.4 | Documentation Changes 4 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
84 | 4.1.5 | Documentation Changes 5 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
85 | 4.1.6 | Documentation Changes 6 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
86 | 4.1.7 | Documentation Changes 7 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
87 | 4.1.8 | Documentation Changes 8 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
88 | 4.1.9 | Documentation Changes 9 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
89 | 4.1.10 | Documentation Changes 10 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
90 | 4.1.11 | Documentation Changes 11 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
91 | 4.1.12 | Documentation Changes 12 | 2.4 | $ | 90 | $ | 216 | [5 empty] | 0.8 | 1 | 1 | 3 | 2.4
92 | 5 | Closing | [7 empty] | $ | 1920 | 0.73846
93 | 5.1 | Sign Off the Contract
94 | 5.2 | Develop Lessons Learned Document | 8 | $ | 120 | $ | 960 | $ | 960 |  |  |  | 8 | 1 | 1 | 1 | 8
95 | 5.3 | Presentation of final product | 8 | $ | 120 | $ | 960 | $ | 960 |  |  |  | 8 | 1 | 1 | 1 | 8
Total Expenses | [10 empty] | 143088 | 55.0338
Contingency Reserve | [10 empty] | 116912 | 44.9662
Total Budget | [10 empty] | 260000
Note on D6: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.