## Sheet1
Project Name: Heartland Equestrian Centre App | [15 empty] | Project Schedule
Equine Development Inc.
|  | Start Week | 2023-09-20
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Starting | 2023-09-20 | 2023-09-27 | 2023-10-04 | 2023-10-11 | 2023-10-18 | 2023-10-25 | 2023-11-01 | 2023-11-08 | 2023-11-15 | 2023-11-22 | 2023-11-29 | 2023-12-06 | 2023-12-13 | 2023-12-20 | 2023-12-27 | 2024-01-03 | 2024-01-10 | 2024-01-17 | 2024-01-24 | 2024-01-31 | Notes
| 2023-09-20 | 2023-09-27 | 2023-10-04 | 2023-10-11 | 2023-10-18 | 2023-10-25 | 2023-11-01 | 2023-11-08 | 2023-11-15 | 2023-11-22 | 2023-11-29 | 2023-12-06 | 2023-12-13 | 2023-12-20 | 2023-12-27 | 2024-01-03 | 2024-01-10 | 2024-01-17 | 2024-01-24 | 2024-01-31
Initiating Phase | 2023-09-20: Sign Contract with Stakeholders; 2023-11-15: Getting Funds; 2024-01-31: P R O J E C T E N D
Develop SWOT Analysis
Develop Project Background & Objectives
Develop Problem/Opportunity Statement
Develop Critical Assumptions and Constraints
Analyze Options and Recommendations
Develop Financial Analysis
Planing Phase | 2023-10-25: Develop Scope Statement
Prepare Budget Estimate
Develop Cost Model
Develop Cost Baseline
Develop Project Schedule
List Potential Risks
Executing Phase | 2023-11-15: Sprint 1
[9 empty] | Milestone: |  | Sprint 2
Sprint 3
Sprint 4
Monitoring | 2023-12-27: Team Meetings
Status Report
Documentation Changes